## Slide 2: Planning Timeline
Important Dates for the 2023 Lenten Season

## Slide 3: Planning Timeline
Nov. 1, 2022: Last day to decrease or cancel orders.
Jan. 13, 2023: Orders ship.
February 22, 2023: Ash Wednesday.
March 27, 2023: Last day orders can be placed to arrive by Easter.
April 9, 2023: Easter Sunday.
Aug. 31, 2023: Lent 2023 Revenue Reporting Form and diocesan remittance due to CRS.

## Slide 4: November 2022
CRS will review donations for Rice Bowl 2022 sent directly to CRS with the information on your Revenue Reporting Form. If more than 75% of the total gifts from your diocese have been received by CRS, we will send you a check to add to the 25% retained for local use.
Review the 25% Guidelines at crsricebowl.org/diocese.
See what’s new with CRS Rice Bowl by visiting crsricebowl.org.

## Slide 5: December 2022
The promotion kit is mailed to diocesan directors in all participating dioceses.
  Contains tips for promotion, including samples of materials. You can also find resources online at crsricebowl.org/diocese.
Recruit volunteers to help you contact parishes and schools. Encourage them to participate in CRS Rice Bowl.
Nov. 1, 2022: Last chance to cancel/reduce orders—materials are packed late November! Materials can always be ordered or increased.

## Slide 6: December 2022
Ensure all parishes and schools in your diocese have placed their orders for free CRS Rice Bowl materials. To order materials:
  Call 800-222-0025.
  Visit crsricebowl.org/order.
Ask your bishop to review and adapt the Bishop’s Endorsement Letter to be sent to faith communities. This can be found at crsricebowl.org/diocese.

## Slide 7: January 2023
This year’s materials are shipped to parishes and schools on Jan. 13, 2023. Orders may still be placed throughout the Lenten season!
Host a CRS Rice Bowl information session for CRS Rice Bowl coordinators.
  Show the “How to Kick Off CRS Rice Bowl” video on crsricebowl.org/parishes.
Place a CRS Rice Bowl web banner on your diocesan website or include an ad in your diocesan paper. These can be found at crsricebowl.org/diocese.

## Slide 8: February 2023
In-Person Activities
Encourage CRS Rice Bowl coordinators to ensure each family receives a CRS Rice Bowl. Ash Wednesday is February 22, 2023!
Host a CRS Rice Bowl kickoff event in your diocese. Take photos and use #CRSRiceBowl and #CRSPlatodeArroz on social media channels.
If you cannot distribute CRS Rice Bowls due to COVID-19, coordinators can encourage families to visit crsricebowl.org/families to print a DIY CRS Rice Bowl label.

## Slide 9: April 2023
Remind organizations and coordinators of Holy Week resources available at crsricebowl.org/holy-week and crsplatodearroz.org/semana-santa.
Refer CRS Rice Bowl coordinators to the video, “How to Collect CRS Rice Bowls,” for tips on hosting a prayerful CRS Rice Bowl collection.

## Slide 10: April 2023
CRS will mail a “Turn in your CRS Rice Bowls” packet to parishes and schools that ordered materials. This includes information on how to collect contributions and return them to their diocesan office. This can also be found on the CRS Rice Bowl parish or Grades 1-8 website. Ensure parishes and schools receive this packet and know where they should send their donations.
Ask your bishop to adapt and send the Bishop’s Thank You Letter.
Post a diocesan Thank You Ad on your diocesan website or paper. The ad can be found at crsricebowl.org/dioceses.

## Slide 11: May/June 2023
Review revenue reporting and remittance instructions.
CRS will send an email with information on the 2023 Revenue Reporting Form. Information can also be found at crsricebowl.org/revenue.

## Slide 12: August 2023
Publish your diocese’s total donation amount in your diocesan newspaper. Be sure to highlight where your local 25% is used!
By August 31:
  Submit the completed Revenue Reporting Form at http://ricebowl.crs.org/.
  Send 75% of your diocese’s donation to:
Catholic Relief Services
CRS Rice Bowl
PO Box 5200
Harlan, IA 51593-0700

## Slide 13: September 2023
For DD-designated dioceses:
Order Updated Spreadsheets are due October 1.
For IND-designated dioceses (dioceses where parishes and schools update their orders directly with CRS):
A postcard is mailed to parishes and schools at the end of September, encouraging them to update their order for 2024 CRS Rice Bowl materials.
Not sure if you’re IND or DD? Contact crsricebowl@crs.org.

## Slide 14: Thank you!